## Module recommendations
Module | Type | Points | My take | Why relevant to a social network | Effort | Risk | Dependencies / notes
Use a framework for both frontend & backend | Major | 2 | CHOOSE (core) | Faster delivery, consistent architecture, easier auth/CRUD. | M | Low | Pick one stack early (e.g., ASP.NET Core + React/Next).
Allow users to interact with other users | Major | 2 | CHOOSE (core) | Profiles + friends/follows + chat are the heart of a social network. | M–L | Med | Design DB relations early (friendship, blocks, etc.).
Real-time features (WebSockets/SignalR) | Major | 2 | CHOOSE (core) | Needed for chat, presence, live notifications. | M | Med | Implement after auth + basic DB tables; share service layer with HTTP.
Advanced permissions system | Major | 2 | CHOOSE (core) / backup if time | Roles (admin/mod/user) are natural for moderation & safety. | M | Med | Keep scope small: role matrix + backend enforcement.
Notification system (CRUD) | Minor | 1 | CHOOSE | Makes app feel alive; easy demo. | S–M | Low | Store notifications in DB; optionally push via WS.
File upload & management | Minor | 1 | CHOOSE | Avatars, post images. | M | Med | Limit to images, size/type validation, access control.
Multiple languages (3+) | Minor | 1 | CHOOSE / backup | Real product skill; easy points if done early. | S–M | Low | Do from day 1: no hardcoded strings.
Use an ORM (EF Core) | Minor | 1 | CHOOSE (very good with .NET) | Speeds up DB work; reduces SQL boilerplate; safer migrations. | S–M | Low | EF Core + migrations + service layer.
Support additional browsers | Minor | 1 | BACKUP (low coupling) | Easy point: Firefox + Safari/Edge support. | S | Low | Test early; avoid browser-specific APIs.
Advanced search (filters/sort/pagination) | Minor | 1 | BACKUP (great ROI) | Search users/posts/tags is extremely social-network-y. | S–M | Low | Start with DB queries; add full-text later if needed.
OAuth 2.0 remote auth | Minor | 1 | OPTIONAL | Convenient sign-in; relevant for 42/GitHub. | M | Med | Account linking edge cases; do after base auth is stable.
2FA (TOTP) | Minor | 1 | OPTIONAL | Security depth; good learning. | M | Med | Recovery codes + UX; do after base auth is stable.
Data export/import | Minor | 1 | BACKUP | Useful & contained: export profile/posts/messages to JSON/CSV. | S–M | Low | Great independent backup if another module fails.
Custom-made design system with reusable components | Minor | 1 | OPTIONAL | Low backend dependency, Reusable for the whole project |  |  | If you choose a UI library (like Material UI, shadcn/ui, Chakra, etc.), you must be careful: the module wants a custom-made design system, not “we used a library as-is”.
Custom: End-to-end encryption for private messages | Major | 2 |  | Relevant for data protection. |  |  | As it’s a custom module, need a good basis to prove that it’s valid
Voice/speech integration | Minor | 1 | AVOID
ELK log management | Major | 2 | AVOID (no DevOps owner) | High complexity stack; easy to lose weeks. | L | High | Only do if someone owns DevOps + monitoring + retention.
| 12 | 23